## San Ramon 2017
CNH KIWANIS MID-YEAR CONFERENCE NORTH 2017
EVENT REQUIREMENTS
San Ramon Marriott
2600 Bishop Drive, San Ramon, CA 94583 (925) 867-9200
DATE | TIME | EVENT | LOCATION | ROOM SET-UP | FOOD & BEVERAGE | ACCESSORIES/AUDIO VISUAL | Notes
Wednesday, February 1, 2017 |  | Final office preparation for MYN --truck packed - MM to leave for San Ramon
Thursday, February 2, 2017 | 24 Hour Hold | Convention Office To be available 24 hours a day from 6:00 AM Thursday to 12:00 P.M. Sunday | San Ramon Boardroom | Existing Board Room table | None
| 24 Hour Hold | Convention Storage | Mt. Diablo Room | 6' tables around perimeter of the room. Eight chairs | None
| 10:00 A.M. | Pre Con Meeting
| 5:00 -7:00 PM | Foundation Executive Committee Meeting | Pleasanton/Danville | Conference for 10 | Coffee and tea service package for 6 ppl | None
| 5:00 P.M. | Unload van with volunteers
| 6:00 P.M. - 8:00 P.M. | Past Governor's Reception
Friday, February 3, 2017 | 24 Hour Hold | Convention Office To be available 24 hours a day from 6:00 AM Thursday to 12:00 P.M. Sunday | San Ramon Boardroom | Existing Board Room table | None
| 24 Hour Hold | Convention Storage | Mt. Diablo Room | 6' tables around perimeter of the room. Eight chairs | None
| 11:00 A.M. to 11:45 A.M. | Realignment Meeting |  | Existing
| TBD | Committee Meeting | MR 10 | Conference for 20 or U Shape (please space chairs well apart) .
| 10:00 A.M. to 12:00 P.M. | Kiwanis Cal-Nev-Ha Foundation Board Training | Contra Costa Ballroom Salon 1 | Conference for 24 or U Shape (please space chairs well apart) Theater or perimeter seating for 20 in the rear/ sides of the room. | Water service | American Flag teleconference speaker phone
| 12:00 P.M. to 1:00 P.M. | Kiwanis Cal-Nev-Ha Foundation Board Luncheon | Contra Costa Ballroom Salon 1 |  | Modified Deli Buffet per Jeneane $25++
| 1:00 P.M. to 5:00 P.M. | Kiwanis Cal-Nev-Ha Foundation Board Meeting | Contra Costa Ballroom Salon 1 |  | Water service. Assorted sodas on consumption.
| 5:00 P.M. | AV Setup for General Sessions | Bishop Ranch Ballroom A-E | Rounds of 10 for 600 Existing stage with standing podium. Stairs on both sides of stage toward the stage front. One 6' draped table for awards on stage and two 6' draped table to the side of the stage for AV. One 6' draped table on floor for Foundation raffle. Will need table stands for 8 reserved tables in front of stage.
| 7:00 P.M. | AV Setup for Seminar Sessions | Bishop Ranch Ballroom F-H | 8x12x2 stage place one edge of stage on the center line of the room - front of stage must be 20 feet from the back wall for rear projection. Standing podium on stage. One draped table for stage and one draped table for AV. Theater seating to max. Leave 3 openings for wheelchairs /scooters near the door and 2 in the front of the room.
| 7:00 P.M. | AV Setup for Seminar Sessions | Contra Costa Ballroom Salon 1 | 8x12x2 stage place one edge of stage on the center line of the room - front of stage must be 20 feet from the back wall for rear projection. Standing podium on stage. One draped table for stage and one draped table for AV. Theater seating to max. Leave 3 openings for wheelchairs /scooters near the door and 2 in the front of the room.
| 7:00 P.M. | AV Setup for Seminar Sessions | Capitol C | 8x12x2 stage place one edge of stage on the center line of the room - front of stage must be 20 feet from the back wall for rear projection. Standing podium on stage. One draped table for stage and one draped table for AV. Theater seating to max. Leave 3 openings for wheelchairs /scooters near the door and 2 in the front of the room.
| 6:00 P.M. - 7:00 P.M. | AV Setup for Seminar Sessions | Capitol D | 8x12x2 stage place one edge of stage on the center line of the room - front of stage must be 20 feet from the back wall for rear projection. Standing podium on stage. One draped table for stage and one draped table for AV. Theater seating to max. Leave 3 openings for wheelchairs /scooters near the door and 2 in the front of the room.
Saturday, February 4, 2017 | 24 Hour Hold | Convention Office To be available 24 hours a day from 6:00 AM Thursday to 12:00 P.M. Sunday | San Ramon Boardroom | Existing Board Room table | None
| 24 Hour Hold | Convention Storage | Mt. Diablo Room | 6' tables around perimeter of the room. Eight chairs | None
| 6:00 A.M. | Staff begins set up of Registration area | Bishop Ranch Ballroom foyer |  |  | Need four eight foot tables for pre-reg area and two eight foot tables for on site reg. Need classroom tables in back of registration tables. 4 Easels in registration area for signs. Cork board or display board for message center. Power must be accessible to reg tables.
| 6:00 A.M. - 7:30 A.M. | Decorator Completes General Session set up | Bishop Ranch Ballroom A-E
| 6:30 A.M. to 7:30 A.M. | Set Up for Exhibitors | Bishop Ranch Ballroom foyer
| 6:45 A.M. | Registration opens for Rose Float Breakfast only | Contra Costa Ballroom Salon 1 | Need draped registration table and two chairs inside entrance
| 7:00 A.M. - 8:00 A.M. | Kiwanis Club of the Rose Float Pasadena Breakfast | Contra Costa Ballroom Salon 1 | Rounds of 10 for 100 ppl. Two reserved tables near podium. Need draped 8' table near podium for drawing prizes. Small Table for AV. |  | American Flag. Standing podium
| 6:45 A.M. - 4:00 P.M. | Volunteer Check-in & Information Booth Manned | Bishop Ranch Ballroom foyer
| 7:00 A.M. | Volunteer AV Crew meets with Mark McDonald or Bruce Hennings | Mt. Diablo Room | Existing
| 7:30 A.M. - 1:30 P.M. | Registration Open | Bishop Ranch Ballroom foyer | Existing |  |  | Will be closed for Inter-club Luncheon - will need two host volunteers to man tables
| 7:30 A.M. - 4:00 P.M. | District Sales & Exhibit Display Tables Open | Bishop Ranch Ballroom foyer | 30-40 Six foot tables needed for displays. Need power accessible to designated tables
| 8:00 A.M. - 8:50 A.M. | General Session | Bishop Ranch Ballroom A-E | Linens: White Rounds of 10 for 640 Existing stage with standing podium . Stairs on both sides of stage toward the stage front. One 6' draped table for awards on stage and two 6' draped table to the side of the stage for AV. Will need table stands for 8 reserved tables in front of stage. | Water service. | American Flag on stage. Standing podium with mic. Matrix Mobile will provide AV services. | Need diagram of room
| 9:00 AM-9:50 A.M. | Seminar - See Seminar Grid | Bishop Ranch Ballroom A-E | See AV Set Up Friday 6:00 P.M. | Water Service in rooms.
| 9:00 AM-4:00 P.M. | Seminar - See Seminar Grid | Bishop Ranch Ballroom F-H | See AV Set Up Friday 6:00 P.M.
| 9:00 AM-4:00 P.M. | Seminar - See Seminar Grid | Contra Costa Ballroom Salon 1 | See AV Set Up Friday 6:00 P.M.
| 9:00 AM-4:00 P.M. | Seminar - See Seminar Grid | Contra Costa Ballroom Salon 2 | See AV Set Up Friday 6:00 P.M.
| 9:00 AM-4:00 P.M. | Seminar - See Seminar Grid | Pleasanton Room | See AV Set Up Friday 6:00 P.M.
| 9:00 AM-4:00 P.M. | Seminar - See Seminar Grid | Danville Room | See AV Set Up Friday 6:00 P.M.
| 9:00 AM-4:00 P.M. | Seminar - See Seminar Grid | Feather | See AV Set Up Friday 6:00 P.M.
| 9:00 AM-10:50 A.M. | Kiwanis Cal-Nev-Ha Foundation Seminar | Contra Costa Ballroom Salon 2 | Rounds of 10, table top podium and small table for AV | Water Service in rooms.
| 11:00 AM-11:50 A.M. | Foundation Ambassadors | Contra Costa Ballroom Salon 2 | Existing | Water Service in rooms.
| 10:00 AM-2:50 P.M. | Meeting of the 2016-2017 Lt. Governors-elect | Pleasanton Room | Theatre for 20. Head table for 2. Located photographer in alcove. Water service on head table. | Water Service in rooms. | Kiwanis to provide own screens and AV equipment
| 10:00 AM-2:50 P.M. | Photos of 2016-2017 Lt. Governors-elect & Staff photos
| 10:45 a.m.-11:45 a.m. | Decorations Committee has access to Ballroom | Bishop Ranch Ballroom A-E
| Doors Open at Noon. Doors Open - Call to Order at 12:15 P.M. - Luncheon served at 12:20 P.M. Adjourn at 1:30 P.M. | Inter-Club Luncheon, Host club-the Kiwanis Club of Moraga Valley, Moraga, Pres. Sam Sperry | Bishop Ranch Ballroom A-E | Rounds of 10 for 600. Existing stage. One 6' draped table for drawing to the side of stage and two 6' draped table to the side of the stage for AV. Will need table stands for 8 reserved tables in front of stage. | Menu: Per contract Linen colors: White with white napkins. Notes: Preset salad & dessert. Servers to collect tickets. Only tickets stamped VEGETARIAN should receive veggie meals. Serve head table & reserved tables first. All service in room stop when entrees have been served. | American Flag. Hilding Larson to provide audio/visual services. | Vegetarian meal tickets will be labeled with a "Vegetarian Meal" label
| 11:00 to 11:50 A.M. | 2016-2017 Lt. Governors Team Meeting | Danville Room | Set theater style to max; leave 3 openings for wheelchairs/scooters near the door and 2 in the front of the room; head table for 4, table top podium and small table for AV | Water service only
| 2:30 - 5:00 P.M. | Staff and volunteers breakdown registration & load van
| 4:00-4:45 P.M. | Closing Session | Bishop Ranch Ballroom A-D | Existing
| 5:00 - 6:00 P.M. | Governor's Reception for Lt. Governors and Cabinet | Governor's Suite
| 4:00-6:00 PM | Circle K Key to College | Pleasanton/Danville
| 5:30 - 6:30 PM | Accelerate Reception (Private event) | Contra Costa Ballroom Salon 2 | Reception style. Scattered lowboys with seating for 30 ppl | TBD Contracted price is $22++
| 4:00 - 6:00 PM | Silent Auction Set Up | Contra Costa Ballroom Salon 1 | 3 - 8' tables for the silent auction
| 6:15 - 7:15 PM | No-Host Social & Silent Auction | Contra Costa Ballroom Salon 1 | 3 - 8' tables for the silent auction | Cash bar(s) location TBD
| 7:20 PM Welcome 7:30 PM Dinner Service Begins | Foundation Kids Bash: Let’s Be Kids Again! | Bishop Ranch Ballroom Salon D | Rounds of 10 for 120. 2 - 8' reception tables with 4 chairs inside ballroom. Will need table stands for 2 reserved tables in front of stage. 2 - 8' tables to one side of the stage for wine/gift auction. Stage, podium and AV will be the same as earlier sessions. Linen colors TBD | Garden Salad; Chicken Provencal: breast of chicken topped with diced tomatoes, mushrooms, capers and lemon sauce; Chefs choice of starch; oven roasted vegetables; New York cheesecake for dessert | Hotel to provide: American Flag Hilding Larson to provide AV. Room layout TBD
| 9:30 PM - 12:00 AM | Final move out for AV
Sunday, February 5, 2017 | 24 Hour Hold | Convention Office To be available 24 hours a day from 6:00 AM Thursday to 12:00 P.M. Sunday | San Ramon Boardroom | Existing Board Room table | None
Bolded events have F&B requirements -- see BEO |  |  |  |  | Our cost will be $35.00 ++
Korean Beef Bulgogi Skewer……
Shaded events are not confirmed
This shading indicates a Foundation event
This shading indicates a Foundation event which is NOT confirmed